## Summary
Metric | Value
Report | Agentic QE Platform - MVP - Cycle report
Cycle | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE (CYC-4, incremental)
Status | completed
Baseline | BL-1 v2
SUT build | demo/hotel-booking-platform-v2
Requirements | 138
Delta | 20 unchanged · 3 enhanced · 20 new
Test cases | 13
Test cases by type | {"functional":8,"non-functional":5}
Test cases by label | {"functional":8,"eqe":13,"automation":8,"regression":13,"non-functional":5}
Scripts | 7
Executed (real) | 8
Passed | 8
Failed | 0
Pass rate % | 100
Execution tool | Playwright 1.63.0 (headless Chromium, JSON reporter)
Defects | 3
Coverage (passing %) | 5.1
Narrative | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE (incremental) worked from Jira epic AQPI-32, AQPI-23 (Jira export on GitHub), Codebase sri465inno/uc-agentic-quality-engineering@demo/hotel-booking-platform-v2 (fe1ce44) (pulled live from GitHub). The reviewed requirement set holds 138 requirements (20 unchanged · 3 enhanced · 20 new). 13 test cases are designed, 8 of them automated in 7 Playwright scripts. Execution ran 8 automated cases for real: 8 passed and 0 failed (pass rate 100%). 3 defect(s) were raised from real failures: DEF-001 AQPI-8 4.2 Sort and filter hotel results: asked for in Jira but not implemented in the code; DEF-002 AQPI-13 5.3 Explain and control personalization: asked for in Jira but not implemented in the code; DEF-003 AQPI-22 7.4 Show booking outcome: asked for in Jira but not implemented in the code.
Narrative drafted by | Deterministic template (demo mode - no model API key set)
AI mode | rule-based (no model API key set)

## Inputs
Input | Reference | Statements | Provenance | Provenance detail
Jira epic | AQPI-32, AQPI-23 | 33 | jira-export | Jira export on GitHub (sri465inno/uc-agentic-quality-engineering@demo/jira-export, release-2.0 snapshot): Jira REST API v3 JSON of AQPI-32, exported from https://tcs-team-ou6drgfr.atlassian.net; no live Jira call was made
Codebase | sri465inno/uc-agentic-quality-engineering@demo/hotel-booking-platform-v2 (fe1ce44) | 13 | github | Pulled live from GitHub: git clone of sri465inno/uc-agentic-quality-engineering@demo/hotel-booking-platform-v2 (fe1ce44) at 2026-10-11T16:15:57.789Z

## Requirements
ID | Jira | Requirement | Type | Source | Business rule | Rule | Exact values | Test approach | Status | Version | Superseded value | AI title (suggested) | AI summary (suggested) | AI acceptance criteria (suggested)
REQ-001 | AQPI-1 | A guest can complete the complete search-to-confirmation flow using valid inputs. | functional | jira-only | BR-001 | Search-to-confirmation journey |  | Automatable | carried over | 1
REQ-002 | AQPI-1 | Only bookable inventory and valid rates are presented as available. | functional | jira-only | BR-002 | Only bookable inventory is offered |  | Automatable | carried over | 1
REQ-003 | AQPI-1 | Total price is disclosed before confirmation, including mandatory taxes and fees. | functional | jira-only | BR-003 | Total price disclosed before confirmation |  | Automatable | carried over | 1
REQ-004 | AQPI-1 | Ancillary offers do not block booking when declined or unavailable. | functional | jira-only | BR-004 | Offers never block the booking |  | Automatable | carried over | 1
REQ-005 | AQPI-1 | The platform prevents or safely handles duplicate reservation submissions. | functional | jira-only | BR-005 | Duplicate submissions handled safely |  | Automatable | carried over | 1
REQ-006 | AQPI-1 | A successful reservation produces a durable confirmation identifier. | functional | jira-only | BR-006 | Durable confirmation identifier |  | Automatable | carried over | 1
REQ-007 | AQPI-1 | Confirmation is displayed on screen and an email request is generated. | functional | jira-only | BR-007 | Confirmation shown and e-mail requested |  | Automatable | carried over | 1
REQ-008 | AQPI-1 | Required business and technical events are logged using approved identifiers and masking rules. | functional | jira-only | BR-008 | Required business and technical events are logged |  | Manual | carried over | 1
REQ-009 | AQPI-2, AQPI-6, AQPI-10, AQPI-14, AQPI-18, AQPI-23, AQPI-27 | All child user stories meet their acceptance criteria and the Definition of Done. | functional | jira-only | BR-009 | All child user stories meet their acceptance |  | Manual | unchanged | 1
REQ-010 | AQPI-2, AQPI-6, AQPI-10, AQPI-14, AQPI-18, AQPI-23, AQPI-27 | Negative and error paths for each story are tested and evidenced. | functional | jira-only | BR-010 | Negative and error paths for each story |  | Manual | unchanged | 1
REQ-011 | AQPI-2, AQPI-6, AQPI-10, AQPI-14, AQPI-18, AQPI-23, AQPI-27 | Required logging is in place and verified free of sensitive data. | functional | jira-only | BR-011 | Required logging is in place and verified |  | Manual | unchanged | 1
REQ-012 | AQPI-2, AQPI-6, AQPI-10, AQPI-14, AQPI-18, AQPI-23, AQPI-27 | The Product Owner has accepted the capability end to end. | functional | jira-only | BR-012 | The Product Owner has accepted the capability |  | Manual | unchanged | 1
REQ-013 | AQPI-3 | Given valid search criteria, when the guest submits the search, then a search request is created and matching available hotels are returned. | functional | jira-only | BR-013 | Hotel search |  | Automatable | carried over | 1
REQ-014 | AQPI-3 | The submitted criteria remain visible and editable on the results page. | functional | jira-only | BR-014 | Search criteria stay visible |  | Automatable | carried over | 1
REQ-015 | AQPI-3 | Past check-in dates, check-out dates not after check-in, and missing mandatory fields are rejected with actionable messages. | functional | jira-only | BR-015 | Search date and mandatory field validation |  | Automatable | carried over | 1
REQ-016 | AQPI-3 | A no-availability result explains that no matching inventory was found and allows criteria changes. | non-functional | jira-only | BR-016 | No availability |  | Automatable | carried over | 1
REQ-017 | AQPI-3 | Check-in must precede check-out. | functional | jira-only | BR-017 | Check-in must precede check-out |  | Manual | carried over | 1
REQ-018 | AQPI-3 | Occupancy must comply with configured room limits. | functional | jira-only | BR-018 | Occupancy must comply with configured room limits |  | Manual | carried over | 1
REQ-019 | AQPI-3 | Maximum stay length must be configurable. | functional | jira-only | BR-019 | Maximum stay length must be configurable |  | Manual | carried over | 1
REQ-020 | AQPI-4 | Required fields are clearly identified. | functional | jira-only | BR-020 | Search form required fields |  | Automatable | carried over | 1
REQ-021 | AQPI-4 | Invalid combinations return field-level messages. | functional | jira-only | BR-021 | Field-level validation messages |  | Automatable | carried over | 1
REQ-022 | AQPI-4 | Server validation is authoritative when client and server results differ. | functional | jira-only | BR-022 | Server validation is authoritative when client and |  | Manual | carried over | 1
REQ-023 | AQPI-4 | Validation messages are accessible to assistive technology. | non-functional | jira-only | BR-023 | Validation messages are accessible to assistive technology |  | Manual | carried over | 1
REQ-024 | AQPI-4 | Validation rules must be configurable where market or property rules vary. | functional | jira-only | BR-024 | Validation rules must be configurable where market |  | Manual | carried over | 1
REQ-025 | AQPI-5 | Zero results provide options to alter dates, occupancy, destination, or filters. | functional | jira-only | BR-025 | No availability |  | Automatable | carried over | 1
REQ-026 | AQPI-5 | Technical failures display a non-technical message and retry option. | functional | jira-only | BR-026 | Technical failures display a non-technical message and |  | Manual | carried over | 1
REQ-027 | AQPI-5 | Repeated submission does not create inconsistent sessions. | functional | jira-only | BR-027 | Consistent search sessions |  | Automatable | carried over | 1
REQ-028 | AQPI-7 | Each result shows hotel name, location, representative image, starting price, currency, and availability indicator. | non-functional | jira-only | BR-028 | Result card content |  | Automatable | carried over | 1
REQ-029 | AQPI-7 | Mandatory fees or pricing qualifications are clearly disclosed. | functional | jira-only | BR-029 | Pricing qualification disclosed |  | Automatable | carried over | 1
REQ-030 | AQPI-7 | Unavailable hotels are not presented as immediately bookable. | functional | jira-only | BR-030 | Unavailable hotels not bookable |  | Automatable | carried over | 1
REQ-031 | AQPI-7 | Results support pagination or progressive loading. | functional | jira-only | BR-031 | Result pagination |  | Automatable | carried over | 1
REQ-032 | AQPI-7 | Displayed starting price must correspond to a valid rate returned for the search criteria. | functional | jira-only | BR-032 | Starting price backed by a valid rate |  | Automatable | carried over | 1
REQ-033 | AQPI-9 | Hotel description, images, location, amenities, room options, pricing, major policies, and relevant restrictions are displayed. | functional | jira-only | BR-033 | Hotel details page |  | Automatable | carried over | 1
REQ-034 | AQPI-9 | The guest can select a valid room and rate plan. | functional | jira-only | BR-034 | The guest can select a valid room |  | Manual | carried over | 1
REQ-035 | AQPI-9 | If inventory changes, the guest is informed before continuing. | functional | jira-only | BR-035 | If inventory changes, the guest is informed |  | Manual | carried over | 1
REQ-036 | AQPI-9 | Rate conditions and cancellation terms must be shown before selection. | functional | jira-only | BR-036 | Rate conditions shown before selection |  | Automatable | carried over | 1
REQ-037 | AQPI-11 | The service considers available context such as stay dates, season, destination, hotel, room, party composition, declared interests, and consented profile attributes. | functional | jira-only | BR-037 | The service considers available context such as |  | Manual | carried over | 1
REQ-038 | AQPI-11 | Unavailable or ineligible products are excluded. | functional | jira-only | BR-038 | Ineligible offers excluded |  | Automatable | carried over | 1
REQ-039 | AQPI-11 | The service returns a reason code for each recommended item. | functional | jira-only | BR-039 | Reason code per recommendation |  | Automatable | carried over | 1
REQ-040 | AQPI-11 | When personalization data is unavailable, safe contextual defaults may be returned. | functional | jira-only | BR-040 | When personalization data is unavailable, safe contextual |  | Manual | carried over | 1
REQ-041 | AQPI-11 | Sensitive traits must not be inferred or used. | functional | jira-only | BR-041 | Sensitive traits must not be inferred or |  | Manual | carried over | 1
REQ-042 | AQPI-11 | Personalization must honor consent and data-retention rules. | functional | jira-only | BR-042 | Personalization must honor consent and data-retention rules |  | Manual | carried over | 1
REQ-043 | AQPI-11 | Business rules and model versions must be auditable. | functional | jira-only | BR-043 | Business rules and model versions must be |  | Manual | carried over | 1
REQ-044 | AQPI-12 | Each offer shows name, description, price, currency, applicability, and any restrictions. | functional | jira-only | BR-044 | Offer content and optional-extra label |  | Automatable | carried over | 1
REQ-045 | AQPI-12 | The guest can add, skip, or dismiss an offer. | functional | jira-only | BR-045 | Add, skip or dismiss an offer |  | Automatable | carried over | 1
REQ-046 | AQPI-12 | Offers are clearly distinguished from mandatory fees. | functional | jira-only | BR-046 | Offer content and optional-extra label |  | Automatable | carried over | 1
REQ-047 | AQPI-12 | Failure to load offers does not block room booking. | functional | jira-only | BR-047 | Offers never block the booking |  | Automatable | carried over | 1
REQ-048 | AQPI-15 | The cart contains hotel, room, rate plan, stay dates, occupancy, quantity, currency, and price components. | functional | jira-only | BR-048 | Cart contents |  | Automatable | carried over | 1
REQ-049 | AQPI-15 | Inventory and price are revalidated when required. | functional | jira-only | BR-049 | Inventory and price are revalidated when required |  | Manual | carried over | 1
REQ-050 | AQPI-15 | The cart has a defined expiration and displays relevant timeout behavior. | functional | jira-only | BR-050 | The cart has a defined expiration and |  | Manual | carried over | 1
REQ-051 | AQPI-15 | A cart must not itself create a reservation. | functional | jira-only | BR-051 | A cart must not itself create a |  | Manual | carried over | 1
REQ-052 | AQPI-15 | Price-change handling must require guest acknowledgement when material. | functional | jira-only | BR-052 | Price-change handling must require guest acknowledgement when |  | Manual | carried over | 1
REQ-053 | AQPI-16 | The guest can add an available ancillary. | functional | jira-only | BR-053 | The guest can add an available ancillary |  | Manual | carried over | 1
REQ-054 | AQPI-16 | Supported quantities can be changed within product limits. | functional | jira-only | BR-054 | Extra quantity limits |  | Automatable | carried over | 1
REQ-055 | AQPI-16 | Removal updates totals immediately. | functional | jira-only | BR-055 | Removing an extra updates totals |  | Automatable | carried over | 1
REQ-056 | AQPI-16 | Ineligible or sold-out products cannot be retained silently. | functional | jira-only | BR-056 | Ineligible or sold-out products cannot be retained |  | Manual | carried over | 1
REQ-057 | AQPI-17 | Room charges, taxes, mandatory fees, optional products, discounts, and total are itemized. | functional | jira-only | BR-057 | Itemised cart total |  | Automatable | carried over | 1
REQ-058 | AQPI-17 | Currency is consistently displayed. | functional | jira-only | BR-058 | Currency is consistently displayed |  | Manual | carried over | 1
REQ-059 | AQPI-17 | Material changes are highlighted and require acknowledgement. | functional | jira-only | BR-059 | Material changes are highlighted and require acknowledgement |  | Manual | carried over | 1
REQ-060 | AQPI-17 | The guest can return to edit supported selections. | functional | jira-only | BR-060 | The guest can return to edit supported |  | Manual | carried over | 1
REQ-061 | AQPI-17 | The final payable total must be revalidated before reservation submission. | functional | jira-only | BR-061 | The final payable total must be revalidated |  | Manual | carried over | 1
REQ-062 | AQPI-19 | Required and optional fields are clearly distinguished. | functional | jira-only | BR-062 | Required and optional guest fields |  | Automatable | carried over | 1
REQ-063 | AQPI-19 | Inputs are validated and error messages are accessible. | non-functional | jira-only | BR-063 | Guest input validation |  | Automatable | carried over | 1
REQ-064 | AQPI-19 | The guest receives applicable privacy notice and consent controls. | functional | jira-only | BR-064 | Privacy notice required |  | Automatable | carried over | 1
REQ-065 | AQPI-19 | Data is transmitted securely and is not exposed in client logs. | functional | jira-only | BR-065 | Data is transmitted securely and is not |  | Manual | carried over | 1
REQ-066 | AQPI-19 | Data minimization applies. | functional | jira-only | BR-066 | Data minimization applies |  | Manual | carried over | 1
REQ-067 | AQPI-19 | Sensitive values must be masked in support tools and excluded from analytics logs. | functional | jira-only | BR-067 | Sensitive values masked for support |  | Automatable | carried over | 1
REQ-068 | AQPI-20 | The guest sees the final payable or guarantee amount before authorization. | functional | jira-only | BR-068 | Payable amount before authorisation |  | Automatable | carried over | 1
REQ-069 | AQPI-20 | Payment data is handled through approved secure components. | functional | jira-only | BR-069 | Payment data is handled through approved secure |  | Manual | carried over | 1
REQ-070 | AQPI-20 | Authorization success, decline, timeout, and technical failure are handled distinctly. | functional | jira-only | BR-070 | Distinct payment outcomes |  | Automatable | carried over | 1
REQ-071 | AQPI-20 | The product does not store prohibited card data in application logs. | functional | jira-only | BR-071 | No raw card data accepted |  | Automatable | carried over | 1
REQ-072 | AQPI-20 | Payment requirements depend on rate conditions. | functional | jira-only | BR-072 | Payment requirements depend on rate conditions |  | Manual | carried over | 1
REQ-073 | AQPI-20 | Retry behavior must avoid duplicate authorization. | functional | jira-only | BR-073 | Retry behavior must avoid duplicate authorization |  | Manual | carried over | 1
REQ-074 | AQPI-21 | A successful request creates one reservation and returns a confirmation identifier. | functional | jira-only | BR-074 | One reservation per successful request |  | Automatable | carried over | 1
REQ-075 | AQPI-21 | Repeated submissions with the same idempotency key do not create duplicate reservations. | functional | jira-only | BR-075 | Idempotent reservation |  | Automatable | carried over | 1
REQ-076 | AQPI-21 | Inventory, price, payment, and reservation outcomes remain reconcilable. | functional | jira-only | BR-076 | Outcomes reconcilable |  | Automatable | carried over | 1
REQ-077 | AQPI-21 | Partial failures trigger defined recovery or manual-review handling. | functional | jira-only | BR-077 | Partial failures trigger defined recovery or manual-review |  | Manual | carried over | 1
REQ-078 | AQPI-21 | Reservation submission must use an idempotency mechanism. | functional | jira-only | BR-078 | Reservation submission must use an idempotency mechanism |  | Manual | carried over | 1
REQ-079 | AQPI-21 | The source of truth for confirmation status must be defined. | functional | jira-only | BR-079 | The source of truth for confirmation status |  | Manual | carried over | 1
REQ-080 | AQPI-24 | The message contains guest-safe confirmation details, hotel information, stay dates, booked items, pricing summary, and applicable policy information. | functional | jira-only | BR-080 | Confirmation e-mail content |  | Automatable | unchanged | 1
REQ-081 | AQPI-24 | The message content matches the confirmed reservation state. | functional | jira-only | BR-081 | Confirmation e-mail content |  | Automatable | unchanged | 1
REQ-082 | AQPI-24 | Templates support required locale and accessibility standards. | non-functional | jira-only | BR-082 | Templates support required locale and accessibility standards |  | Manual | unchanged | 1
REQ-083 | AQPI-24 | Only necessary personal data may be included. | functional | jira-only | BR-083 | Only necessary personal data may be included |  | Manual | unchanged | 1
REQ-084 | AQPI-24 | Sensitive payment details must not appear. | functional | jira-only | BR-084 | Confirmation e-mail content |  | Automatable | unchanged | 1
REQ-085 | AQPI-25 | A successful reservation creates one confirmation-email request. | functional | jira-only | BR-085 | A successful reservation creates one confirmation-email request |  | Manual | unchanged | 1
REQ-086 | AQPI-25 | Send failure does not reverse a valid reservation. | functional | jira-only | BR-086 | E-mail failure does not undo the booking |  | Automatable | unchanged | 1
REQ-087 | AQPI-25 | Permitted retries avoid duplicate or excessive messages. | functional | jira-only | BR-087 | Permitted retries avoid duplicate or excessive messages |  | Manual | carried over | 1
REQ-088 | AQPI-25 | Operational users can distinguish queued, sent, delivered, bounced, and failed states when supported by the provider. | functional | jira-only | BR-088 | Operational users can distinguish queued, sent, delivered, |  | Manual | unchanged | 1
REQ-089 | AQPI-25 | Email addresses must be masked outside authorized operational views. | functional | jira-only | BR-089 | Email addresses must be masked outside authorized |  | Manual | unchanged | 1
REQ-090 | AQPI-26 | The request verifies sufficient reservation information without exposing data. | functional | jira-only | BR-090 | Resend reveals nothing |  | Automatable | unchanged | 1
REQ-091 | AQPI-26 | Rate limits and abuse controls apply. | functional | jira-only | BR-091 | Rate limits and abuse controls apply |  | Manual | unchanged | 1
REQ-092 | AQPI-26 | The resend creates a new message event without creating a new reservation. | functional | jira-only | BR-092 | The resend creates a new message event |  | Manual | unchanged | 1
REQ-093 | AQPI-28 | Sensitive data is classified and mapped to approved storage and processing locations. | functional | jira-only | BR-093 | Sensitive data is classified and mapped to |  | Manual | carried over | 1
REQ-094 | AQPI-28 | Data is encrypted in transit and at rest where required. | functional | jira-only | BR-094 | Data is encrypted in transit and at |  | Manual | carried over | 1
REQ-095 | AQPI-28 | Logs and analytics exclude or mask prohibited fields. | functional | jira-only | BR-095 | Logs and analytics exclude or mask prohibited |  | Manual | carried over | 1
REQ-096 | AQPI-28 | Access to operational data is role-based and auditable. | functional | jira-only | BR-096 | Sensitive values masked for support |  | Automatable | carried over | 1
REQ-097 | AQPI-28 | Retention and deletion follow approved policy. | functional | jira-only | BR-097 | Retention and deletion follow approved policy |  | Manual | carried over | 1
REQ-098 | AQPI-29 | Events use a correlation ID across supported services. | functional | jira-only | BR-098 | Correlation ID across services |  | Automatable | carried over | 1
REQ-099 | AQPI-29 | Business events and technical logs are distinguishable. | functional | jira-only | BR-099 | Business events and technical logs are distinguishable |  | Manual | carried over | 1
REQ-100 | AQPI-29 | Metrics and alerts exist for agreed critical failures and latency. | non-functional | jira-only | BR-100 | Metrics and alerts exist for agreed critical |  | Manual | carried over | 1
REQ-101 | AQPI-29 | Logging degradation does not expose sensitive payloads or silently block booking unless explicitly required. | functional | jira-only | BR-101 | Logging degradation does not expose sensitive payloads |  | Manual | carried over | 1
REQ-102 | AQPI-29 | Event schemas must be versioned. | functional | jira-only | BR-102 | Event schemas must be versioned |  | Manual | carried over | 1
REQ-103 | AQPI-29 | Production log access must be controlled and retained according to policy. | functional | jira-only | BR-103 | Production log access must be controlled and |  | Manual | carried over | 1
REQ-104 | AQPI-30 | Keyboard navigation, focus order, labels, instructions, status messaging, and error handling are accessible. | non-functional | jira-only | BR-104 | Keyboard navigation, focus order, labels, instructions, status |  | Manual | carried over | 1
REQ-105 | AQPI-30 | Visual information is not conveyed by color alone. | functional | jira-only | BR-105 | Visual information is not conveyed by color |  | Manual | carried over | 1
REQ-106 | AQPI-30 | Dynamic updates are announced appropriately. | functional | jira-only | BR-106 | Dynamic updates are announced appropriately |  | Manual | carried over | 1
REQ-107 | AQPI-30 | Email templates are readable and structurally accessible. | non-functional | jira-only | BR-107 | Accessible e-mail template |  | Automatable | carried over | 1
REQ-108 | AQPI-31 | Search, pricing, cart, checkout, reservation, and email dependencies have agreed performance targets. | non-functional | jira-only | BR-108 | Search, pricing, cart, checkout, reservation, and email |  | Manual | carried over | 1
REQ-109 | AQPI-31 | Timeout, retry, circuit-breaker, and fallback behavior are documented. | functional | jira-only | BR-109 | Timeout, retry, circuit-breaker, and fallback behavior are |  | Manual | carried over | 1
REQ-110 | AQPI-31 | Load, resilience, and recovery tests cover critical journeys. | functional | jira-only | BR-110 | Load, resilience, and recovery tests cover critical |  | Manual | carried over | 1
REQ-111 | AQPI-31 | Reservation integrity is prioritized over non-critical personalization and analytics. | functional | jira-only | BR-111 | Reservation integrity is prioritized over non-critical personalization |  | Manual | carried over | 1
REQ-112 | AQPI-33 | A cart expires 20 minutes after it is created and never creates a reservation itself. | functional | agreed | BR-112 | Cart expiry and no implicit reservation | minutes=20 | Automatable | enhanced | 2 | A cart expires 30 minutes after it is created and never creates a reservation itself.
REQ-113 | AQPI-17 | A price change of more than 1% must be acknowledged by the guest before checkout. | functional | code-only | BR-113 | Material price change acknowledgement | pct=1 | Automatable | unchanged | 1
REQ-114 | AQPI-35 | A confirmation can be resent at most 5 times per booking in 24 hours. | functional | agreed | BR-114 | Resend rate limit | limit=5; hours=24 | Automatable | enhanced | 2 | A confirmation can be resent at most 3 times per booking in 24 hours.
REQ-115 | AQPI-21 | Every reservation request needs an Idempotency-Key of 8 to 64 characters; a replay within 24 hours returns the original outcome. | functional | code-only | BR-115 | Idempotency-Key required | min=8; max=64; hours=24 | Automatable | unchanged | 1
REQ-116 | AQPI-34 | A stay can be at most 30 nights; Paris (PAR) allows at most 14 nights. | functional | agreed | BR-116 | Maximum stay length | max=30; par=14 | Automatable | enhanced | 2 | A stay can be at most 30 nights; Paris (PAR) allows at most 21 nights.
REQ-117 | AQPI-4 | Each room holds at most 4 adults and 3 children, and one search books 1 to 8 rooms. | functional | code-only | BR-117 | Occupancy and room limits | adults=4; children=3; rooms=8 | Automatable | unchanged | 1
REQ-118 | AQPI-4 | Check-in can be at most 500 days ahead. | functional | code-only | BR-118 | Booking horizon | days=500 | Automatable | unchanged | 1
REQ-119 | AQPI-32 | Release 1.0 behaviour not named in this epic is unchanged and passes regression. | functional | jira-only | BR-119 | Release 1.0 behaviour not named in this | value1=1 | Manual | new | 1
REQ-120 | AQPI-32 | The Product Owner has accepted the release 2.0 changes end to end. | functional | jira-only | BR-120 | The Product Owner has accepted the release | value1=2 | Manual | new | 1
REQ-121 | AQPI-36 | A confirmed reservation on a refundable rate can be cancelled free of charge up to 48 hours before check-in; a later cancellation is refused and the reservation stays confirmed. | functional | agreed | BR-121 | Free cancellation window | hours=48 | Automatable | new | 1
REQ-122 | AQPI-36 | A cancelled reservation shows status CANCELLED, its payment authorisation is voided and its rooms are released. | functional | agreed | BR-122 | Cancellation voids payment and releases rooms |  | Automatable | new | 1
REQ-123 | AQPI-36 | A reservation on a non-refundable rate cannot be cancelled free of charge and stays confirmed. | functional | jira-only | BR-123 | Non-refundable rates are not cancelled free of charge |  | Automatable | new | 1
REQ-124 | AQPI-24 | The confirmation e-mail of a refundable booking states its free-cancellation deadline, 48 hours before check-in. | functional | agreed | BR-124 | Confirmation states the free-cancellation deadline | hours=48 | Automatable | new | 1
REQ-125 | AQPI-25 | Operations can retry a failed confirmation e-mail at most 3 times; a further retry is refused. | functional | agreed | BR-125 | Operational e-mail retry limit | limit=3 | Automatable | new | 1
REQ-126 | AQPI-37 | A cancelled reservation gets one cancellation e-mail; cancelling it again does not send another. | functional | agreed | BR-126 | One cancellation e-mail per cancelled booking |  | Automatable | new | 1
REQ-127 | AQPI-37 | A cancellation e-mail that cannot be sent does not undo the cancellation. | functional | agreed | BR-127 | Cancellation e-mail failure does not undo the cancellation |  | Automatable | new | 1
REQ-128 | AQPI-37 | Operational users see the cancellation e-mail with its own delivery state, separate from the confirmation. | functional | jira-only | BR-128 | Operational users see the cancellation e-mail with |  | Manual | new | 1
REQ-129 | AQPI-8 | The guest can apply supported filters such as price range, amenities, hotel category, and distance when data is available. | functional | jira-only | BR-129 | Result filters |  | Automatable | new | 1
REQ-130 | AQPI-8 | The guest can sort using approved options. | functional | jira-only | BR-130 | Approved sort options |  | Automatable | new | 1
REQ-131 | AQPI-8 | Selected criteria are visible and removable. | functional | jira-only | BR-131 | Selected criteria are visible and removable |  | Manual | new | 1
REQ-132 | AQPI-8 | Zero results after filtering offer a reset option. | functional | jira-only | BR-132 | Reset after filtering to zero |  | Automatable | new | 1
REQ-133 | AQPI-13 | The interface identifies when offers are personalized where required. | functional | jira-only | BR-133 | The interface identifies when offers are personalized |  | Manual | new | 1
REQ-134 | AQPI-13 | The guest can proceed without selecting ancillary products. | functional | jira-only | BR-134 | Proceed without extras |  | Automatable | new | 1
REQ-135 | AQPI-13 | A consent or preference change affects future eligible recommendations according to policy. | functional | jira-only | BR-135 | Consent drives personalization |  | Automatable | new | 1
REQ-136 | AQPI-22 | Success displays confirmation identifier, hotel, stay summary, selected products, and total. | functional | jira-only | BR-136 | Booking outcome content |  | Automatable | new | 1
REQ-137 | AQPI-22 | A failure does not display a false confirmation. | functional | jira-only | BR-137 | No false confirmation |  | Automatable | new | 1
REQ-138 | AQPI-22 | Unknown or timeout states instruct the guest not to resubmit blindly and provide a safe recovery path. | functional | jira-only | BR-138 | Safe guidance in unknown states |  | Automatable | new | 1

## Test Cases
Key | Name | Objective | Precondition | Test Step | Test Data | Expected Result | Priority | Type | Labels | Requirement link | Automation status | Cycle | Change | Revision note
TC-F-001 | Guest books a pay-at-hotel room with breakfast from search to confirmation e-mail | Verify the whole guest journey across all six services: search, hotel details, offers, cart, extra, payment summary, reservation and confirmation e-mail. | The six hotel services are running with their seeded catalogue (reset before the case). | 1. Search NYC for the standard stay 2. Open the chosen hotel 3. Get recommended extras 4. Create a cart and add breakfast 5. Read the payment summary 6. Submit the reservation 7. Open the confirmation e-mail | search.destination=NYC; selection.ratePlanCode=FLEX; extras.code=BREAKFAST; extras.quantity=1; every other booking attribute from the hotel data dictionary examples | HTTP 201 CONFIRMED with a confirmation number; e-mail generated with the same number and total; cart total = payment summary total = booked total | Medium | Functional | functional, eqe, automation, regression | AQPI-1, REQ-001, BR-001 | Automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over
TC-F-002 | Guest books a prepaid non-refundable room in Paris and pays now | Verify the prepaid journey: the payment summary asks for the full amount now and the booking confirms. | The six hotel services are running with their seeded catalogue (reset before the case). | 1. Search PAR 2. Create a cart for the prepaid rate 3. Check pay-now equals the total 4. Submit the reservation | search.destination=PAR; selection.hotelId=H-PAR-001; selection.roomCode=STD-K; selection.ratePlanCode=SAVER; every other booking attribute from the hotel data dictionary examples | Payment summary pay-now = total; HTTP 201 CONFIRMED | Medium | Functional | functional, eqe, automation, regression | AQPI-1, REQ-001, BR-001 | Automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over
TC-F-003 | A sold-out hotel is shown as unavailable and cannot be put in a cart | Verify that a hotel with no rooms left is not offered as bookable and that trying to book it is refused. | The six hotel services are running with their seeded catalogue (reset before the case). Inventory of the chosen hotel is set to 0. | 1. Set the hotel inventory to 0 2. Search 3. Try to create a cart for that hotel | selection.hotelId=H-NYC-001; every other booking attribute from the hotel data dictionary examples | Result shows availability SOLD_OUT, bookable false, no starting price; cart creation returns HTTP 409 ROOM_NO_LONGER_AVAILABLE | Medium | Functional | functional, eqe, automation, regression | AQPI-1, REQ-002, BR-002 | Automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over
TC-F-004 | An unavailable extra is refused and the room still books | Verify that an extra that cannot be sold is refused clearly while the room reservation still succeeds. | The six hotel services are running with their seeded catalogue (reset before the case). LATE_CHECKOUT is marked unavailable. | 1. Mark LATE_CHECKOUT unavailable 2. Create a cart 3. Try to add LATE_CHECKOUT 4. Submit the reservation | extras.code=LATE_CHECKOUT; extras.quantity=1; every other booking attribute from the hotel data dictionary examples | Adding the extra returns HTTP 422 EXTRA_NOT_AVAILABLE; reservation HTTP 201 CONFIRMED | Medium | Functional | functional, eqe, automation, regression | AQPI-1, REQ-004, BR-004 | Automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over
TC-F-005 | A double-clicked Book button creates one reservation and one payment | Verify that two simultaneous submissions with the same idempotency key produce one reservation and one authorisation. | The six hotel services are running with their seeded catalogue (reset before the case). | 1. Create a cart 2. Submit the reservation twice at the same time with one key 3. Read the payments ledger | request.idempotencyKeyPrefix=aqe-double; every other booking attribute from the hotel data dictionary examples | Both responses name the same reservation; exactly one payment authorisation exists | High | Functional | functional, eqe, automation, regression | AQPI-1, REQ-005, BR-005 | Automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over
TC-F-006 | The confirmation number can be looked up again after booking | Verify the confirmation identifier is stored with the reservation and returned on later reads. | The six hotel services are running with their seeded catalogue (reset before the case). | 1. Book the standard stay 2. Read the reservation back by id | Standard booking: every other booking attribute from the hotel data dictionary examples | HTTP 201 with a 10-character HB… number; GET /api/reservations/{id} returns the same number and CONFIRMED | Medium | Functional | functional, eqe, automation, regression | AQPI-1, REQ-006, BR-006 | Automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over
TC-F-007 | The guest sees the booking outcome and one confirmation e-mail is created | Verify the outcome the guest sees and that exactly one confirmation e-mail request exists. | The six hotel services are running with their seeded catalogue (reset before the case). | 1. Book the standard stay 2. Read the outcome 3. List the messages for the reservation | Standard booking: every other booking attribute from the hotel data dictionary examples | Outcome headline says the booking is confirmed; one CONFIRMATION message for the reservation | Medium | Functional | functional, eqe, automation, regression | AQPI-1, REQ-007, BR-007 | Automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over
TC-N-001 | Verify: Validation messages are accessible to assistive technology | Confirm the behaviour "Validation messages are accessible to assistive technology." (no executable template in the catalogue - manual verification). | Access to the system under test and its operational logs. | 1. Perform the action described by the requirement 2. Observe the outcome in the system or its logs | n/a | Validation messages are accessible to assistive technology. | High | Non-functional | non-functional, eqe, regression | AQPI-4, REQ-023, BR-023 | Not automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over
TC-F-008 | An unavailable extra is refused and the room still books | Verify that an extra that cannot be sold is refused clearly while the room reservation still succeeds. | The six hotel services are running with their seeded catalogue (reset before the case). LATE_CHECKOUT is marked unavailable. | 1. Mark LATE_CHECKOUT unavailable 2. Create a cart 3. Try to add LATE_CHECKOUT 4. Submit the reservation | extras.code=LATE_CHECKOUT; extras.quantity=1; every other booking attribute from the hotel data dictionary examples | Adding the extra returns HTTP 422 EXTRA_NOT_AVAILABLE; reservation HTTP 201 CONFIRMED | Medium | Functional | functional, eqe, automation, regression | AQPI-12, REQ-047, BR-047 | Automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over
TC-N-002 | Verify: Templates support required locale and accessibility standards | Confirm the behaviour "Templates support required locale and accessibility standards." (no executable template in the catalogue - manual verification). | Access to the system under test and its operational logs. | 1. Perform the action described by the requirement 2. Observe the outcome in the system or its logs | n/a | Templates support required locale and accessibility standards. | Low | Non-functional | non-functional, eqe, regression | AQPI-24, REQ-082, BR-082 | Not automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over
TC-N-003 | Verify: Metrics and alerts exist for agreed critical failures and latency | Confirm the behaviour "Metrics and alerts exist for agreed critical failures and latency." (no executable template in the catalogue - manual verification). | Access to the system under test and its operational logs. | 1. Perform the action described by the requirement 2. Observe the outcome in the system or its logs | n/a | Metrics and alerts exist for agreed critical failures and latency. | Low | Non-functional | non-functional, eqe, regression | AQPI-29, REQ-100, BR-100 | Not automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over
TC-N-004 | Verify: Keyboard navigation, focus order, labels, instructions, status messaging, and error handling are accessible | Confirm the behaviour "Keyboard navigation, focus order, labels, instructions, status messaging, and error handling are accessible." (no executable template in the catalogue - manual verification). | Access to the system under test and its operational logs. | 1. Perform the action described by the requirement 2. Observe the outcome in the system or its logs | n/a | Keyboard navigation, focus order, labels, instructions, status messaging, and error handling are accessible. | Low | Non-functional | non-functional, eqe, regression | AQPI-30, REQ-104, BR-104 | Not automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over
TC-N-005 | Verify: Search, pricing, cart, checkout, reservation, and email dependencies have agreed performance targets | Confirm the behaviour "Search, pricing, cart, checkout, reservation, and email dependencies have agreed performance targets." (no executable template in the catalogue - manual verification). | Access to the system under test and its operational logs. | 1. Perform the action described by the requirement 2. Observe the outcome in the system or its logs | n/a | Search, pricing, cart, checkout, reservation, and email dependencies have agreed performance targets. | Low | Non-functional | non-functional, eqe, regression | AQPI-31, REQ-108, BR-108 | Not automated | Hotel booking release 2.0 (AQPI-32 + AQPI-23) · EQE | Carried over

## Execution
Case | Requirement | Name | Result | Duration ms | Note | AI triage (suggested; result unchanged)
TC-F-001 | REQ-001 | Guest books a pay-at-hotel room with breakfast from search to confirmation e-mail | passed | 1108
TC-F-002 | REQ-001 | Guest books a prepaid non-refundable room in Paris and pays now | passed | 136
TC-F-003 | REQ-002 | A sold-out hotel is shown as unavailable and cannot be put in a cart | passed | 84
TC-F-004 | REQ-004 | An unavailable extra is refused and the room still books | passed | 93
TC-F-005 | REQ-005 | A double-clicked Book button creates one reservation and one payment | passed | 69
TC-F-006 | REQ-006 | The confirmation number can be looked up again after booking | passed | 67
TC-F-007 | REQ-007 | The guest sees the booking outcome and one confirmation e-mail is created | passed | 74
TC-N-001 | REQ-023 | Verify: Validation messages are accessible to assistive technology | not-run | 0 | Manual test case - not automated, not executed
TC-F-008 | REQ-047 | An unavailable extra is refused and the room still books | passed | 73
TC-N-002 | REQ-082 | Verify: Templates support required locale and accessibility standards | not-run | 0 | Manual test case - not automated, not executed
TC-N-003 | REQ-100 | Verify: Metrics and alerts exist for agreed critical failures and latency | not-run | 0 | Manual test case - not automated, not executed
TC-N-004 | REQ-104 | Verify: Keyboard navigation, focus order, labels, instructions, status messaging, and error handling are accessible | not-run | 0 | Manual test case - not automated, not executed
TC-N-005 | REQ-108 | Verify: Search, pricing, cart, checkout, reservation, and email dependencies have agreed performance targets | not-run | 0 | Manual test case - not automated, not executed

## Defects
ID | Title | Severity | Story | Jira defect | Case | Requirement | Expected | Actual | Failing assertion | Movement | AI triage | AI summary (drafted) | AI steps to reproduce | AI likely cause
DEF-001 | AQPI-8 4.2 Sort and filter hotel results: asked for in Jira but not implemented in the code | Minor | AQPI-8 | not raised in Jira |  |  | Code implements AQPI-8 (4 acceptance criteria) | No code in demo/hotel-booking-platform mentions AQPI-8 |  | implemented in code, not yet verified by a test of this testing type
DEF-002 | AQPI-13 5.3 Explain and control personalization: asked for in Jira but not implemented in the code | Minor | AQPI-13 | not raised in Jira |  |  | Code implements AQPI-13 (3 acceptance criteria) | No code in demo/hotel-booking-platform mentions AQPI-13 |  | implemented in code, not yet verified by a test of this testing type
DEF-003 | AQPI-22 7.4 Show booking outcome: asked for in Jira but not implemented in the code | Minor | AQPI-22 | not raised in Jira |  |  | Code implements AQPI-22 (3 acceptance criteria) | No code in demo/hotel-booking-platform mentions AQPI-22 |  | implemented in code, not yet verified by a test of this testing type

## Fixed and certified
ID | Title | Story | Case | First seen | Retested in | Result | Status | Certification

## Coverage
Requirement | Text | Cases | Automated | Executed | Failed | Status
REQ-001 | A guest can complete the complete search-to-confirmation flow using valid inputs. | 2 | 2 | 2 | 0 | executed - passing
REQ-002 | Only bookable inventory and valid rates are presented as available. | 1 | 1 | 1 | 0 | executed - passing
REQ-003 | Total price is disclosed before confirmation, including mandatory taxes and fees. | 0 | 0 | 0 | 0 | not covered
REQ-004 | Ancillary offers do not block booking when declined or unavailable. | 1 | 1 | 1 | 0 | executed - passing
REQ-005 | The platform prevents or safely handles duplicate reservation submissions. | 1 | 1 | 1 | 0 | executed - passing
REQ-006 | A successful reservation produces a durable confirmation identifier. | 1 | 1 | 1 | 0 | executed - passing
REQ-007 | Confirmation is displayed on screen and an email request is generated. | 1 | 1 | 1 | 0 | executed - passing
REQ-008 | Required business and technical events are logged using approved identifiers and masking rules. | 0 | 0 | 0 | 0 | not covered
REQ-009 | All child user stories meet their acceptance criteria and the Definition of Done. | 0 | 0 | 0 | 0 | not covered
REQ-010 | Negative and error paths for each story are tested and evidenced. | 0 | 0 | 0 | 0 | not covered
REQ-011 | Required logging is in place and verified free of sensitive data. | 0 | 0 | 0 | 0 | not covered
REQ-012 | The Product Owner has accepted the capability end to end. | 0 | 0 | 0 | 0 | not covered
REQ-013 | Given valid search criteria, when the guest submits the search, then a search request is created and matching available hotels are returned. | 0 | 0 | 0 | 0 | not covered
REQ-014 | The submitted criteria remain visible and editable on the results page. | 0 | 0 | 0 | 0 | not covered
REQ-015 | Past check-in dates, check-out dates not after check-in, and missing mandatory fields are rejected with actionable messages. | 0 | 0 | 0 | 0 | not covered
REQ-016 | A no-availability result explains that no matching inventory was found and allows criteria changes. | 0 | 0 | 0 | 0 | not covered
REQ-017 | Check-in must precede check-out. | 0 | 0 | 0 | 0 | not covered
REQ-018 | Occupancy must comply with configured room limits. | 0 | 0 | 0 | 0 | not covered
REQ-019 | Maximum stay length must be configurable. | 0 | 0 | 0 | 0 | not covered
REQ-020 | Required fields are clearly identified. | 0 | 0 | 0 | 0 | not covered
REQ-021 | Invalid combinations return field-level messages. | 0 | 0 | 0 | 0 | not covered
REQ-022 | Server validation is authoritative when client and server results differ. | 0 | 0 | 0 | 0 | not covered
REQ-023 | Validation messages are accessible to assistive technology. | 1 | 0 | 0 | 0 | designed only (manual)
REQ-024 | Validation rules must be configurable where market or property rules vary. | 0 | 0 | 0 | 0 | not covered
REQ-025 | Zero results provide options to alter dates, occupancy, destination, or filters. | 0 | 0 | 0 | 0 | not covered
REQ-026 | Technical failures display a non-technical message and retry option. | 0 | 0 | 0 | 0 | not covered
REQ-027 | Repeated submission does not create inconsistent sessions. | 0 | 0 | 0 | 0 | not covered
REQ-028 | Each result shows hotel name, location, representative image, starting price, currency, and availability indicator. | 0 | 0 | 0 | 0 | not covered
REQ-029 | Mandatory fees or pricing qualifications are clearly disclosed. | 0 | 0 | 0 | 0 | not covered
REQ-030 | Unavailable hotels are not presented as immediately bookable. | 0 | 0 | 0 | 0 | not covered
REQ-031 | Results support pagination or progressive loading. | 0 | 0 | 0 | 0 | not covered
REQ-032 | Displayed starting price must correspond to a valid rate returned for the search criteria. | 0 | 0 | 0 | 0 | not covered
REQ-033 | Hotel description, images, location, amenities, room options, pricing, major policies, and relevant restrictions are displayed. | 0 | 0 | 0 | 0 | not covered
REQ-034 | The guest can select a valid room and rate plan. | 0 | 0 | 0 | 0 | not covered
REQ-035 | If inventory changes, the guest is informed before continuing. | 0 | 0 | 0 | 0 | not covered
REQ-036 | Rate conditions and cancellation terms must be shown before selection. | 0 | 0 | 0 | 0 | not covered
REQ-037 | The service considers available context such as stay dates, season, destination, hotel, room, party composition, declared interests, and consented profile attributes. | 0 | 0 | 0 | 0 | not covered
REQ-038 | Unavailable or ineligible products are excluded. | 0 | 0 | 0 | 0 | not covered
REQ-039 | The service returns a reason code for each recommended item. | 0 | 0 | 0 | 0 | not covered
REQ-040 | When personalization data is unavailable, safe contextual defaults may be returned. | 0 | 0 | 0 | 0 | not covered
REQ-041 | Sensitive traits must not be inferred or used. | 0 | 0 | 0 | 0 | not covered
REQ-042 | Personalization must honor consent and data-retention rules. | 0 | 0 | 0 | 0 | not covered
REQ-043 | Business rules and model versions must be auditable. | 0 | 0 | 0 | 0 | not covered
REQ-044 | Each offer shows name, description, price, currency, applicability, and any restrictions. | 0 | 0 | 0 | 0 | not covered
REQ-045 | The guest can add, skip, or dismiss an offer. | 0 | 0 | 0 | 0 | not covered
REQ-046 | Offers are clearly distinguished from mandatory fees. | 0 | 0 | 0 | 0 | not covered
REQ-047 | Failure to load offers does not block room booking. | 1 | 1 | 1 | 0 | executed - passing
REQ-048 | The cart contains hotel, room, rate plan, stay dates, occupancy, quantity, currency, and price components. | 0 | 0 | 0 | 0 | not covered
REQ-049 | Inventory and price are revalidated when required. | 0 | 0 | 0 | 0 | not covered
REQ-050 | The cart has a defined expiration and displays relevant timeout behavior. | 0 | 0 | 0 | 0 | not covered
REQ-051 | A cart must not itself create a reservation. | 0 | 0 | 0 | 0 | not covered
REQ-052 | Price-change handling must require guest acknowledgement when material. | 0 | 0 | 0 | 0 | not covered
REQ-053 | The guest can add an available ancillary. | 0 | 0 | 0 | 0 | not covered
REQ-054 | Supported quantities can be changed within product limits. | 0 | 0 | 0 | 0 | not covered
REQ-055 | Removal updates totals immediately. | 0 | 0 | 0 | 0 | not covered
REQ-056 | Ineligible or sold-out products cannot be retained silently. | 0 | 0 | 0 | 0 | not covered
REQ-057 | Room charges, taxes, mandatory fees, optional products, discounts, and total are itemized. | 0 | 0 | 0 | 0 | not covered
REQ-058 | Currency is consistently displayed. | 0 | 0 | 0 | 0 | not covered
REQ-059 | Material changes are highlighted and require acknowledgement. | 0 | 0 | 0 | 0 | not covered
REQ-060 | The guest can return to edit supported selections. | 0 | 0 | 0 | 0 | not covered
REQ-061 | The final payable total must be revalidated before reservation submission. | 0 | 0 | 0 | 0 | not covered
REQ-062 | Required and optional fields are clearly distinguished. | 0 | 0 | 0 | 0 | not covered
REQ-063 | Inputs are validated and error messages are accessible. | 0 | 0 | 0 | 0 | not covered
REQ-064 | The guest receives applicable privacy notice and consent controls. | 0 | 0 | 0 | 0 | not covered
REQ-065 | Data is transmitted securely and is not exposed in client logs. | 0 | 0 | 0 | 0 | not covered
REQ-066 | Data minimization applies. | 0 | 0 | 0 | 0 | not covered
REQ-067 | Sensitive values must be masked in support tools and excluded from analytics logs. | 0 | 0 | 0 | 0 | not covered
REQ-068 | The guest sees the final payable or guarantee amount before authorization. | 0 | 0 | 0 | 0 | not covered
REQ-069 | Payment data is handled through approved secure components. | 0 | 0 | 0 | 0 | not covered
REQ-070 | Authorization success, decline, timeout, and technical failure are handled distinctly. | 0 | 0 | 0 | 0 | not covered
REQ-071 | The product does not store prohibited card data in application logs. | 0 | 0 | 0 | 0 | not covered
REQ-072 | Payment requirements depend on rate conditions. | 0 | 0 | 0 | 0 | not covered
REQ-073 | Retry behavior must avoid duplicate authorization. | 0 | 0 | 0 | 0 | not covered
REQ-074 | A successful request creates one reservation and returns a confirmation identifier. | 0 | 0 | 0 | 0 | not covered
REQ-075 | Repeated submissions with the same idempotency key do not create duplicate reservations. | 0 | 0 | 0 | 0 | not covered
REQ-076 | Inventory, price, payment, and reservation outcomes remain reconcilable. | 0 | 0 | 0 | 0 | not covered
REQ-077 | Partial failures trigger defined recovery or manual-review handling. | 0 | 0 | 0 | 0 | not covered
REQ-078 | Reservation submission must use an idempotency mechanism. | 0 | 0 | 0 | 0 | not covered
REQ-079 | The source of truth for confirmation status must be defined. | 0 | 0 | 0 | 0 | not covered
REQ-080 | The message contains guest-safe confirmation details, hotel information, stay dates, booked items, pricing summary, and applicable policy information. | 0 | 0 | 0 | 0 | not covered
REQ-081 | The message content matches the confirmed reservation state. | 0 | 0 | 0 | 0 | not covered
REQ-082 | Templates support required locale and accessibility standards. | 1 | 0 | 0 | 0 | designed only (manual)
REQ-083 | Only necessary personal data may be included. | 0 | 0 | 0 | 0 | not covered
REQ-084 | Sensitive payment details must not appear. | 0 | 0 | 0 | 0 | not covered
REQ-085 | A successful reservation creates one confirmation-email request. | 0 | 0 | 0 | 0 | not covered
REQ-086 | Send failure does not reverse a valid reservation. | 0 | 0 | 0 | 0 | not covered
REQ-087 | Permitted retries avoid duplicate or excessive messages. | 0 | 0 | 0 | 0 | not covered
REQ-088 | Operational users can distinguish queued, sent, delivered, bounced, and failed states when supported by the provider. | 0 | 0 | 0 | 0 | not covered
REQ-089 | Email addresses must be masked outside authorized operational views. | 0 | 0 | 0 | 0 | not covered
REQ-090 | The request verifies sufficient reservation information without exposing data. | 0 | 0 | 0 | 0 | not covered
REQ-091 | Rate limits and abuse controls apply. | 0 | 0 | 0 | 0 | not covered
REQ-092 | The resend creates a new message event without creating a new reservation. | 0 | 0 | 0 | 0 | not covered
REQ-093 | Sensitive data is classified and mapped to approved storage and processing locations. | 0 | 0 | 0 | 0 | not covered
REQ-094 | Data is encrypted in transit and at rest where required. | 0 | 0 | 0 | 0 | not covered
REQ-095 | Logs and analytics exclude or mask prohibited fields. | 0 | 0 | 0 | 0 | not covered
REQ-096 | Access to operational data is role-based and auditable. | 0 | 0 | 0 | 0 | not covered
REQ-097 | Retention and deletion follow approved policy. | 0 | 0 | 0 | 0 | not covered
REQ-098 | Events use a correlation ID across supported services. | 0 | 0 | 0 | 0 | not covered
REQ-099 | Business events and technical logs are distinguishable. | 0 | 0 | 0 | 0 | not covered
REQ-100 | Metrics and alerts exist for agreed critical failures and latency. | 1 | 0 | 0 | 0 | designed only (manual)
REQ-101 | Logging degradation does not expose sensitive payloads or silently block booking unless explicitly required. | 0 | 0 | 0 | 0 | not covered
REQ-102 | Event schemas must be versioned. | 0 | 0 | 0 | 0 | not covered
REQ-103 | Production log access must be controlled and retained according to policy. | 0 | 0 | 0 | 0 | not covered
REQ-104 | Keyboard navigation, focus order, labels, instructions, status messaging, and error handling are accessible. | 1 | 0 | 0 | 0 | designed only (manual)
REQ-105 | Visual information is not conveyed by color alone. | 0 | 0 | 0 | 0 | not covered
REQ-106 | Dynamic updates are announced appropriately. | 0 | 0 | 0 | 0 | not covered
REQ-107 | Email templates are readable and structurally accessible. | 0 | 0 | 0 | 0 | not covered
REQ-108 | Search, pricing, cart, checkout, reservation, and email dependencies have agreed performance targets. | 1 | 0 | 0 | 0 | designed only (manual)
REQ-109 | Timeout, retry, circuit-breaker, and fallback behavior are documented. | 0 | 0 | 0 | 0 | not covered
REQ-110 | Load, resilience, and recovery tests cover critical journeys. | 0 | 0 | 0 | 0 | not covered
REQ-111 | Reservation integrity is prioritized over non-critical personalization and analytics. | 0 | 0 | 0 | 0 | not covered
REQ-112 | A cart expires 20 minutes after it is created and never creates a reservation itself. | 0 | 0 | 0 | 0 | not covered
REQ-113 | A price change of more than 1% must be acknowledged by the guest before checkout. | 0 | 0 | 0 | 0 | not covered
REQ-114 | A confirmation can be resent at most 5 times per booking in 24 hours. | 0 | 0 | 0 | 0 | not covered
REQ-115 | Every reservation request needs an Idempotency-Key of 8 to 64 characters; a replay within 24 hours returns the original outcome. | 0 | 0 | 0 | 0 | not covered
REQ-116 | A stay can be at most 30 nights; Paris (PAR) allows at most 14 nights. | 0 | 0 | 0 | 0 | not covered
REQ-117 | Each room holds at most 4 adults and 3 children, and one search books 1 to 8 rooms. | 0 | 0 | 0 | 0 | not covered
REQ-118 | Check-in can be at most 500 days ahead. | 0 | 0 | 0 | 0 | not covered
REQ-119 | Release 1.0 behaviour not named in this epic is unchanged and passes regression. | 0 | 0 | 0 | 0 | not covered
REQ-120 | The Product Owner has accepted the release 2.0 changes end to end. | 0 | 0 | 0 | 0 | not covered
REQ-121 | A confirmed reservation on a refundable rate can be cancelled free of charge up to 48 hours before check-in; a later cancellation is refused and the reservation stays confirmed. | 0 | 0 | 0 | 0 | not covered
REQ-122 | A cancelled reservation shows status CANCELLED, its payment authorisation is voided and its rooms are released. | 0 | 0 | 0 | 0 | not covered
REQ-123 | A reservation on a non-refundable rate cannot be cancelled free of charge and stays confirmed. | 0 | 0 | 0 | 0 | not covered
REQ-124 | The confirmation e-mail of a refundable booking states its free-cancellation deadline, 48 hours before check-in. | 0 | 0 | 0 | 0 | not covered
REQ-125 | Operations can retry a failed confirmation e-mail at most 3 times; a further retry is refused. | 0 | 0 | 0 | 0 | not covered
REQ-126 | A cancelled reservation gets one cancellation e-mail; cancelling it again does not send another. | 0 | 0 | 0 | 0 | not covered
REQ-127 | A cancellation e-mail that cannot be sent does not undo the cancellation. | 0 | 0 | 0 | 0 | not covered
REQ-128 | Operational users see the cancellation e-mail with its own delivery state, separate from the confirmation. | 0 | 0 | 0 | 0 | not covered
REQ-129 | The guest can apply supported filters such as price range, amenities, hotel category, and distance when data is available. | 0 | 0 | 0 | 0 | not covered
REQ-130 | The guest can sort using approved options. | 0 | 0 | 0 | 0 | not covered
REQ-131 | Selected criteria are visible and removable. | 0 | 0 | 0 | 0 | not covered
REQ-132 | Zero results after filtering offer a reset option. | 0 | 0 | 0 | 0 | not covered
REQ-133 | The interface identifies when offers are personalized where required. | 0 | 0 | 0 | 0 | not covered
REQ-134 | The guest can proceed without selecting ancillary products. | 0 | 0 | 0 | 0 | not covered
REQ-135 | A consent or preference change affects future eligible recommendations according to policy. | 0 | 0 | 0 | 0 | not covered
REQ-136 | Success displays confirmation identifier, hotel, stay summary, selected products, and total. | 0 | 0 | 0 | 0 | not covered
REQ-137 | A failure does not display a false confirmation. | 0 | 0 | 0 | 0 | not covered
REQ-138 | Unknown or timeout states instruct the guest not to resubmit blindly and provide a safe recovery path. | 0 | 0 | 0 | 0 | not covered

## Attribute coverage
Attribute | Description | Varied by cases | Status
search.destination | Destination code the guest searches (demo catalogue: New York, London, Paris) | TC-F-001, TC-F-002 | exercised - passing
stay.checkInOffsetDays | Check-in date as days from today (0 = today) |  | not exercised
stay.nights | Nights between check-in and check-out (PAR allows at most 14) |  | not exercised
occupancy.rooms | Rooms requested |  | not exercised
occupancy.adults | Adults in the party (at least one per room, at most 4 per room) |  | not exercised
occupancy.children | Children in the party (at most 3 per room) |  | not exercised
selection.hotelId | Hotel chosen from the results | TC-F-002, TC-F-003 | exercised - passing
selection.roomCode | Room type chosen on the hotel details page | TC-F-002 | exercised - passing
selection.ratePlanCode | FLEX = pay at hotel with a card guarantee; SAVER = prepaid, non-refundable | TC-F-001, TC-F-002 | exercised - passing
extras.code | Optional ancillary added to the cart (empty = none) | TC-F-001, TC-F-004, TC-F-008 | exercised - passing
extras.quantity | Quantity of the ancillary |  | not exercised
guest.email | Where the confirmation e-mail goes |  | not exercised
payment.token | Token from the secure payment component; raw card numbers are never accepted |  | not exercised
consent.privacyNoticeAccepted | Guest confirmed the privacy notice |  | not exercised
request.idempotencyKeyPrefix | Prefix of the Idempotency-Key sent with a reservation (the full key is 8 to 64 characters) | TC-F-005 | exercised - passing

## Traceability by story
Jira item | Level | Scope | Parent | Summary | Requirements | Test cases | Automated | Passed | Failed | Defects | Status
AQPI-32 | epic | this cycle |  | [Epic 8] Release 2.0 – Booking Rule Changes and Free Cancellation | 0 | 0 | 0 | 0 | 0 |  | not covered
AQPI-33 | story | this cycle | AQPI-32 | 10.1 Shorten the cart hold to 20 minutes | 0 | 0 | 0 | 0 | 0 |  | not covered
AQPI-34 | story | this cycle | AQPI-32 | 10.2 Limit Paris stays to 14 nights | 0 | 0 | 0 | 0 | 0 |  | not covered
AQPI-35 | story | this cycle | AQPI-32 | 10.3 Allow up to 5 confirmation resends | 0 | 0 | 0 | 0 | 0 |  | not covered
AQPI-36 | story | this cycle | AQPI-32 | 10.4 Cancel a reservation free of charge | 0 | 0 | 0 | 0 | 0 |  | not covered
AQPI-23 | epic | this cycle |  | [Epic 6] Confirmation and Notifications | 0 | 0 | 0 | 0 | 0 |  | not covered
AQPI-24 | story | this cycle | AQPI-23 | 8.1 Generate confirmation message | 1 | 1 | 0 | 0 | 0 |  | designed, not executed
AQPI-25 | story | this cycle | AQPI-23 | 8.2 Send and track confirmation email | 0 | 0 | 0 | 0 | 0 |  | not covered
AQPI-26 | story | this cycle | AQPI-23 | 8.3 Resend confirmation safely | 0 | 0 | 0 | 0 | 0 |  | not covered
AQPI-37 | story | this cycle | AQPI-23 | 8.4 Send a cancellation e-mail | 0 | 0 | 0 | 0 | 0 |  | not covered
AQPI-1 | initiative | baseline |  | [Initiative] Intelligent Hotel Shopping and Reservation Experience | 6 | 7 | 7 | 7 | 0 |  | verified
AQPI-4 | story | baseline | AQPI-2 | 3.2 Validate occupancy and stay criteria | 1 | 1 | 0 | 0 | 0 |  | designed, not executed
AQPI-12 | story | baseline | AQPI-10 | 5.2 Display ancillary offers | 1 | 1 | 1 | 1 | 0 |  | verified
AQPI-29 | story | baseline | AQPI-27 | 9.2 Provide end-to-end observability | 1 | 1 | 0 | 0 | 0 |  | designed, not executed
AQPI-30 | story | baseline | AQPI-27 | 9.3 Meet accessibility requirements | 1 | 1 | 0 | 0 | 0 |  | designed, not executed
AQPI-31 | story | baseline | AQPI-27 | 9.4 Meet performance and reliability objectives | 1 | 1 | 0 | 0 | 0 |  | designed, not executed

## Traceability matrix
Jira | Requirement | Requirement text | Rule | Test case | Name | Type | Automation | Test data | Script | Result | Defect | Jira defect
AQPI-1 | REQ-001 | A guest can complete the complete search-to-confirmation flow using valid inputs. | BR-001 | TC-F-001 | Guest books a pay-at-hotel room with breakfast from search to confirmation e-mail | functional | Automated | TD-F-001 | br-001-booking-journey.spec.js | passed
AQPI-1 | REQ-001 | A guest can complete the complete search-to-confirmation flow using valid inputs. | BR-001 | TC-F-002 | Guest books a prepaid non-refundable room in Paris and pays now | functional | Automated | TD-F-002 | br-001-booking-journey.spec.js | passed
AQPI-1 | REQ-002 | Only bookable inventory and valid rates are presented as available. | BR-002 | TC-F-003 | A sold-out hotel is shown as unavailable and cannot be put in a cart | functional | Automated | TD-F-003 | br-002-bookable-inventory.spec.js | passed
AQPI-1 | REQ-004 | Ancillary offers do not block booking when declined or unavailable. | BR-004 | TC-F-004 | An unavailable extra is refused and the room still books | functional | Automated | TD-F-004 | br-004-offers-not-blocking.spec.js | passed
AQPI-1 | REQ-005 | The platform prevents or safely handles duplicate reservation submissions. | BR-005 | TC-F-005 | A double-clicked Book button creates one reservation and one payment | functional | Automated | TD-F-005 | br-005-duplicate-submission.spec.js | passed
AQPI-1 | REQ-006 | A successful reservation produces a durable confirmation identifier. | BR-006 | TC-F-006 | The confirmation number can be looked up again after booking | functional | Automated | TD-F-006 | br-006-durable-confirmation.spec.js | passed
AQPI-1 | REQ-007 | Confirmation is displayed on screen and an email request is generated. | BR-007 | TC-F-007 | The guest sees the booking outcome and one confirmation e-mail is created | functional | Automated | TD-F-007 | br-007-confirmation-shown.spec.js | passed
AQPI-4 | REQ-023 | Validation messages are accessible to assistive technology. | BR-023 | TC-N-001 | Verify: Validation messages are accessible to assistive technology | non-functional | Not automated | TD-N-001 |  | not-run
AQPI-12 | REQ-047 | Failure to load offers does not block room booking. | BR-047 | TC-F-008 | An unavailable extra is refused and the room still books | functional | Automated | TD-F-008 | br-047-offers-not-blocking.spec.js | passed
AQPI-24 | REQ-082 | Templates support required locale and accessibility standards. | BR-082 | TC-N-002 | Verify: Templates support required locale and accessibility standards | non-functional | Not automated | TD-N-002 |  | not-run
AQPI-29 | REQ-100 | Metrics and alerts exist for agreed critical failures and latency. | BR-100 | TC-N-003 | Verify: Metrics and alerts exist for agreed critical failures and latency | non-functional | Not automated | TD-N-003 |  | not-run
AQPI-30 | REQ-104 | Keyboard navigation, focus order, labels, instructions, status messaging, and error handling are accessible. | BR-104 | TC-N-004 | Verify: Keyboard navigation, focus order, labels, instructions, status messaging, and error handling are accessible | non-functional | Not automated | TD-N-004 |  | not-run
AQPI-31 | REQ-108 | Search, pricing, cart, checkout, reservation, and email dependencies have agreed performance targets. | BR-108 | TC-N-005 | Verify: Search, pricing, cart, checkout, reservation, and email dependencies have agreed performance targets | non-functional | Not automated | TD-N-005 |  | not-run

## AI activity
Call | Agent | Purpose | Model | When | OK | Cached | ms | Accepted | Rejected by code | Note | Error

## Approvals
Gate | Decision | By | When | Detail
Requirement set review | approved | Priya Shah | 2026-10-11T16:15:59.183Z | 43 requirements approved; 0 excluded; 0 conflict(s) resolved
Merge into baseline | approved | Sam Lee | 2026-10-11T16:15:59.207Z | 23 requirements, 0 test cases, 0 scripts merged: BL-1 v1 -> v2

## Skills
Skill id | Name | Description | Seen by agents | File
automation-script-conventions | Automation script conventions | How every generated Playwright spec is shaped, named and asserted, so scripts stay reviewable and runnable cycle after cycle. | scripts | automation-script-conventions.md
cycle-report | Test cycle report | The fixed shape of every cycle report, so two cycles can be read side by side without translation. | report | cycle-report.md
defect-reporting | Defect reporting | What a defect must contain before it is raised, so every cycle's defects read the same and are actionable. | defects | defect-reporting.md
incremental-merge | Incremental load and merge rules | How an addition is classified against the baseline and what a human must see before it merges. | delta, requirements, testcases, scripts | incremental-merge.md
input-normalisation | Input normalisation and provenance | How several inputs become one requirement set, and what must be visible about where each statement came from. | normalise, requirements | input-normalisation.md
input-review | Input review before the human gate | What the review agent checks in the project inputs and how it words its suggestions for the reviewer. | review-agent | input-review.md
test-case-authoring | Test case authoring and Zephyr export shape | One house style for every test case, so each cycle exports into Zephyr the same way. | testcases, report | test-case-authoring.md
test-data-generation | Test data generation from the input specs | Every test case gets a complete, spec-conformant data set built from the data dictionary in the codebase input. | testdata | test-data-generation.md
testing-eqe | EQE testing - enterprise end-to-end business flows | Steers the agents to test each business flow end to end across the services, as the user experiences it. | requirements, testcases, testdata, scripts, execution, defects, report | testing-eqe.md
traceability-handover | Traceability hand-over | What each phase owes the next one so the chain from input to defect never breaks in any cycle. | normalise, requirements, testcases, testdata, scripts, execution, defects, report | traceability-handover.md

## Hand-overs
Phase | Skills seen | Hand-over | Missing | Artefacts owed
Normalise (3-way compare) | input-normalisation, traceability-handover | complete |  | statements: delivered; gaps: delivered; conflicts: delivered
| input-review | complete |  | suggestions: delivered
Delta classification | incremental-merge | complete |  | delta: delivered
Requirements agent (requirements with their business rules) | incremental-merge, input-normalisation, testing-eqe, traceability-handover | complete |  | businessRules: delivered; requirements: delivered
Test case agent | incremental-merge, test-case-authoring, testing-eqe, traceability-handover | complete |  | functional: delivered; nonFunctional: delivered; journeys: delivered
Test data agent | test-data-generation, testing-eqe, traceability-handover | complete |  | dataSets: delivered; specConformance: delivered
Automation script agent | automation-script-conventions, incremental-merge, testing-eqe, traceability-handover | complete |  | specs: delivered
Execution agent (Playwright, real run) | testing-eqe, traceability-handover | incomplete | evidence | evidence: missing; results: delivered
Defect agent | defect-reporting, testing-eqe, traceability-handover | complete |  | defects: delivered
Cycle report agent | cycle-report, test-case-authoring, testing-eqe, traceability-handover | complete |  | cycleReport: delivered; comparison: delivered; testCaseExport: delivered

## Adapted this cycle
Lesson applied | Detail
risk-based priority | REQ-023 tested at High priority: defect history - DEF-009 on story AQPI-4